## Executive Summary
Workstream 1 Pain Point Matrix
TotalEnergies SKG Communication Kit
Brutal truth | The interviews do not show a technology gap first. They show an adoption, operating-model, and workflow-integration gap. TSF and SousLeSens are credible, but they need to be made consumable through LifeX, platform mappings, governance metrics, and decision traceability.
Basis of preparation | Prepared from the Workstream 1 stakeholder perspective summary and the archived interview findings synthesis. The workbook packages existing evidence into the missing standalone pain point matrix deliverable.
Top pain themes
1 | LifeX is the proof point | The strongest operational pain is fragmented field evidence that does not yet flow through a semantic decision chain.
2 | Platform boundary must be explicit | TSF should define governed meaning; Cognite, Collibra, Fabric, Power BI, search, and AI should consume it.
3 | Value must be measured | Management needs before / after proof tied to time, risk, CAPEX, OPEX, safety, and reuse.
4 | Governance must become operational | Roles, source ownership, semantic drift, APIs, and catalog handoffs need clear ownership and metrics.
5 | AI needs semantic services | RAG and agents need access to controlled concepts, mappings, provenance, and source evidence.
Recommended immediate actions
1 | Designate LifeX as the first governed semantic data product.
2 | Create the TSF portfolio registry and map priority LifeX assets to owners and platform consumers.
3 | Agree the TSF-to-Cognite and TSF-to-Collibra handoff pattern for LifeX concepts.
4 | Expose a first TSF semantic service or query endpoint for AI / search consumption.
5 | Use the decision framework to separate SKG cases from BI, catalog, RAG, or property graph cases.

## Pain Point Matrix
ID | Pain point | Domain | Stakeholder layer | Stakeholder evidence | Affected roles | Root cause | Business impact | Current workaround | Recommended SKG / TSF response | Priority | Time horizon | Suggested owner | Success metric | Source basis | Status
P01 | Semantic portfolio is hard to navigate | Adoption and communication | Standards and Innovation | Jean-Charles Leclerc: portfolio needs visible business outcomes; archive notes say management cannot navigate what exists. | TSF sponsor, data governance, management sponsors | Semantic work is spread across standards, domains, tooling, and pilots without a business-facing registry. | Sponsors struggle to explain what TSF contains, what is reusable, and why it matters now. | Knowledge remains in expert heads, technical artifacts, and scattered project files. | Create a TSF portfolio registry grouped by business domain, use case, consuming platform, semantic assets, maturity level, and owner. | High | 0-30 days | TSF semantic authority with OneTech data governance | Registry created; 100% of priority LifeX semantic assets mapped to owner, use case, and platform consumer. | Stakeholder perspective summary; archive interview findings. | Open
P02 | Management value is still abstract | Business value and ROI | Standards and Innovation | Benoit Guillermou: management needs concrete examples, scoped deliverables, and reusable materials. | Management sponsors, data officers, platform leads | The semantic message is technically sound but not packaged as decision impact, time saved, risk reduced, or reusable evidence. | Ontology can be perceived as academic or optional, which slows funding and adoption. | Decks explain concepts but need tighter before / after evidence for business users. | Anchor communication around LifeX decision questions, value loops, and validation metrics rather than ontology theory. | High | 0-30 days | OneTech data governance and communication kit owner | Executive deck and one-pager include three LifeX decision questions and three measurable value loops. | Stakeholder perspective summary; executive deck narrative. | Open
P03 | No shared decision framework for when to use SKG | Use case selection | All layers | Archive identifies no decision framework; stakeholders need criteria for ontology versus BI, catalog, RAG, or property graph. | Business owners, architects, data product teams, platform teams | Teams lack a simple gate for fragmented data, cross-team coordination, auditability, standards, and long-term reuse. | Risk of over-engineering simple reporting cases and under-engineering mission-critical semantic cases. | Use case choices are made by local preference, available tooling, or vendor narrative. | Use a 5-question gate: cross-system decision, standards traceability, business impact, reuse over time, vendor-lock-in risk. | High | 0-30 days | Data architecture and TSF semantic authority | Decision framework applied to LifeX and at least three candidate use cases. | Archive executive findings; executive deck decision framework. | Open
P04 | TSF is not wired into the LifeX operational workflow | Operational integration | Operations and Business | Julien Campan: LifeX field evidence flows through local tools; summary frames LifeX as the clearest proof point. | LifeX asset manager, inspectors, operations planners, investment reviewers | Semantic models exist beside the workflow instead of being consumed by the weekly decision cycle. | Field evidence does not become reusable decision intelligence for CAPEX, OPEX, risk, and schedule updates. | Inspection photos, Alteryx, Power BI, Excel, and management memos remain loosely connected. | Create the LifeX semantic data product linking observations, equipment classes, documents, work orders, risk, cost, and decision rationale. | Critical | 0-60 days | LifeX owner with TSF and platform teams | First LifeX decision package traces observation -> concept -> source evidence -> risk / cost impact -> recommendation. | Stakeholder perspective summary; archive LifeX pain points. | Open
P05 | Platform boundary is unclear between TSF and Cognite | Platform positioning | Data Platforms | David Teixugueira-de-Castro: TSF must be positioned inside the data-platform reference model; archive notes management hears conflicting messages. | Cognite programme, modelers, data officers, platform architects | Cognite is framed as an operational graph while TSF is framed as formal semantic authority, but the integration boundary is not explicit enough. | Platform discussions turn into competition instead of a layered architecture. | Cognite contextualization proceeds while semantic governance remains adjacent. | Define TSF as the governed meaning layer consumed by Cognite for LifeX-relevant equipment classes, mappings, and rules. | High | 0-60 days | Cognite programme lead and TSF semantic authority | TSF-to-Cognite mapping pattern agreed for priority LifeX classes and source identifiers. | Stakeholder profile; FAQ platform positioning. | Open
P06 | Manual mapping absorbs delivery effort | Data modeling and mapping | Data Platforms | Bastien Jouret: semantic work matters when it removes manual mapping and supports real use cases. | Modelers, data engineers, business analysts | Source descriptions, tags, standards, and local naming conventions are not aligned through reusable semantic mappings. | Teams spend project time reconciling concepts instead of delivering decision outputs. | Manual mapping and project-specific translation between source data and business terms. | Use TSF mappings to translate non-aligned object descriptions into governed equipment and process concepts. | High | 30-90 days | Data modeling lead with TSF modelers | Reduction in duplicated mappings; priority LifeX equipment families mapped once and reused by consuming platforms. | Stakeholder profile; executive deck problem slide. | Open
P07 | Conceptual model knowledge is lost in implementation | Data modeling and knowledge capture | Standards and Innovation | Josephine Boulanger: conceptual models capture business meaning before it is flattened into implementation artifacts. | Data modelers, business SMEs, data product teams | Business-led conceptual modeling is not always preserved as an explicit semantic asset with ownership and reuse path. | Business meaning is lost when delivery ends as SQL-like schemas, local documents, or platform-specific models. | Business knowledge is reconstructed during each project or held by individual modelers. | Capture conceptual models as TSF assets with business definitions, mappings, validation status, and consumer links. | Medium | 30-90 days | Data exposure and semantic modeling teams | Conceptual model assets linked to TSF concepts and platform outputs for priority use cases. | Stakeholder profile. | Open
P08 | Collibra and TSF perimeter is not explicit | Governance and catalog | Data Platforms | Francois-Xavier Mourot: perimeter between catalog governance and semantic modeling has to be clear. | Catalog owners, data stewards, semantic modelers, data domains | Collibra governs data assets and lineage while TSF governs semantic definitions, but handoffs are not formalized. | Data catalog terms can diverge from semantic definitions, creating parallel governance vocabularies. | Catalog and semantic workstreams advance separately with ad hoc mapping. | Connect Collibra entries to TSF concepts, with clear ownership, lineage, approval, and change-management rules. | High | 30-90 days | Collibra owner and TSF semantic authority | Priority Collibra business objects reference TSF concept IDs and semantic owners. | Stakeholder profile; FAQ Collibra positioning. | Open
P09 | Governance metrics are not yet practical enough | Governance and adoption | Data Platforms | Sonia Vallejo-Vaca: semantic governance must be practical, measurable, and connected to search, EDM, Cognite, and AI agents. | Data strategy, governance teams, platform teams, AI roadmap owners | Semantic governance is not yet translated into operating metrics that platform and AI teams can manage. | Governance remains a principle rather than a management system for reuse, quality, and AI readiness. | Teams discuss governance maturity without a consistent scorecard tied to outputs. | Track semantic asset coverage, platform integration rate, reuse rate, drift issues, audit completeness, and decision package traceability. | High | 30-90 days | Data strategy and governance office | Monthly semantic governance dashboard defined and piloted on LifeX. | Stakeholder profile; executive deck operating model. | Open
P10 | Affiliate data ownership and quality are uneven | Source data readiness | Data Platforms | Pascal Colombani: source ownership, DMP completeness, and quality controls are prerequisites for scaling semantic outputs. | EP data officers, affiliate data owners, platform teams | Data Management Plans, ownership, and data quality maturity vary across affiliates and domains. | Semantic outputs cannot scale reliably if source systems and owners are unclear. | Local remediation before dashboarding or executive reporting. | Tie semantic assets to source-system owners, DMP completeness, quality rules, and readiness criteria before scaling. | Medium | 30-90 days | EP data office with affiliate owners | LifeX source inventory includes owner, quality status, semantic mapping status, and readiness rating. | Stakeholder profile. | Open
P11 | AI teams cannot easily consume ontology assets | AI and API consumption | AI, Search and Operations | Elie Maze: AI teams need semantic assets through usable APIs; archive notes ontology data is not accessible via API today. | AI teams, data scientists, Mistral / LLM users, platform engineers | Semantic assets are not packaged as queryable services that AI pipelines can call. | AI work relies on local prompts, retrieval, and data preparation instead of governed concepts and provenance. | Ad hoc collaboration with semantic experts or local copies of vocabulary. | Expose TSF concepts, mappings, and LifeX semantic graph slices through APIs or query endpoints for AI workflows. | High | 30-90 days | AI platform team and TSF technical owner | First AI workflow consumes TSF concepts through an agreed API or query endpoint. | Stakeholder profile; FAQ AI readiness. | Open
P12 | Search quality depends on weak vocabulary and metadata foundations | Search and document grounding | AI, Search and Operations | Pierre Jallais: search quality depends on vocabulary, metadata, and discoverable semantic resources. | Search team, document owners, data stewards, operational users | Controlled vocabularies and metadata quality are not consistently available at document source. | RAG and enterprise search return relevant text but may miss governed definitions, equipment context, or decision impact. | Search teams compensate with local taxonomies, metadata fixes, and prompt design. | Publish discoverable TSF vocabularies and LifeX concept mappings for search indexing and RAG grounding. | Medium | 30-90 days | Search owner with semantic governance | Search index includes priority TSF vocabulary terms and LifeX aliases; relevance tested on signed questions. | Stakeholder profile; FAQ RAG and SKG positioning. | Open
P13 | Business impact model is incomplete | Business value and ROI | All layers | Archive states semantic graphs need stronger realizable impact modeling for OPEX, CAPEX, revenue, safety, and risk. | Management sponsors, LifeX owner, TSF modelers, finance / planning teams | Ontology assets do not yet make enough business impacts explicit for decision makers. | Leadership cannot see how semantic work changes investment, safety, production, or risk choices. | Benefits are described qualitatively or through broad hypotheses. | Model LifeX impacts as first-class semantic objects: cost, schedule, safety, production, integrity, risk, and decision rationale. | Critical | 0-60 days | LifeX owner, TSF modelers, finance / planning input | Each priority LifeX decision question links to at least one impact object and one source-evidence chain. | Archive executive findings; use case showcase. | Open
P14 | Operating model for semantic delivery is not explicit | Operating model | All layers | Archive quote: semantics will not be heard until the operating model question is answered. | TSF team, domain SMEs, platform teams, governance teams | Roles are not yet formalized across central semantic authority, domain contributors, and platform consumers. | Semantic work remains expert-led and hard to scale beyond individual champions. | Local coordination and informal handoffs between semantic experts and platform teams. | Define central meaning, domain knowledge capture, platform consumption, drift monitoring, and approval workflows. | High | 0-60 days | OneTech data governance with TSF sponsor | Operating model signed for LifeX semantic data product, including RACI and change process. | Archive operating model slide; executive deck operating model. | Open
P15 | Industrialization path after LifeX is not packaged | Scaling and industrialization | Operations and Business | Julien Campan profile frames LifeX as a blueprint that should scale through the Digital Factory once proven. | LifeX owner, Digital Factory, asset teams, platform teams | The scale path from pilot to production to other assets is not described as a repeatable package. | A successful LifeX effort could remain local instead of becoming a reusable enterprise pattern. | Pilot knowledge is transferred through meetings and project artifacts. | Package LifeX semantic data product as a repeatable blueprint with scope, mappings, APIs, governance, metrics, and onboarding steps. | Medium | 60-120 days | LifeX owner with Digital Factory and TSF | Reusable LifeX blueprint created and assessed for one next asset or equipment family. | Stakeholder profile; use case showcase. | Open
P16 | Evidence traceability is weak across decision packages | Decision traceability | Operations and Business | Executive deck and use case showcase emphasize field evidence to decision rationale as the LifeX target chain. | LifeX owner, inspectors, management reviewers, data product teams | Evidence, concepts, rules, and decision rationale are not linked in one auditable chain. | Management decisions take longer to prepare and are harder to defend or reuse across FPSOs. | Analysts manually reconcile reports, dashboards, spreadsheets, and memos. | Build traceability from observation to equipment concept, rule, source evidence, risk / cost impact, and recommendation. | Critical | 0-60 days | LifeX data product owner and semantic modelers | A management decision package can show traceable links from evidence to recommendation for one priority scenario. | Use case showcase; stakeholder summary. | Open

## Stakeholder View
Stakeholder | Layer | Posture | Main pain point | Need / ask | Implication for matrix
Jean-Charles Leclerc | Standards and Innovation | Strong advocate | Portfolio hard to navigate and dispersed across topics. | Focus, prioritization, and V2 wired to a business outcome. | P01, P14
Benoit Guillermou | Standards and Innovation | Institutional supporter | Management needs concrete examples and scoped deliverables. | Translate semantic capability into decision language. | P02, P03
Josephine Boulanger | Standards and Innovation | Strong advocate | Conceptual model meaning can be lost in implementation. | Capture semantic knowledge alongside data exposure deliverables. | P07
David Teixugueira-de-Castro | Data Platforms | Pragmatic / ROI-focused | TSF needs to fit inside the data-platform reference model. | Position TSF as a capability that feeds platform workflows. | P05
Bastien Jouret | Data Platforms | Pragmatic / ROI-focused | Manual mapping and source alignment create delivery friction. | Use semantic work to remove mapping pain in real use cases. | P06
Benoit Soleilhavoup | Data Platforms | Skeptic / ROI gate | Ontology investment needs money, time, or safety proof. | Apply SKG only where the use case requires semantic depth. | P02, P03, P13
Francois-Xavier Mourot | Data Platforms | Pragmatic connector | Catalog governance and semantic modeling perimeter is unclear. | Map TSF business objects into Collibra with clear ownership. | P08
Sonia Vallejo-Vaca | Data Platforms | Institutional supporter | Semantic governance needs practical metrics and platform connection. | Connect semantic governance to search, EDM, Cognite, and agents. | P09
Pascal Colombani | Data Platforms | Governance-first pragmatist | Affiliate source ownership and quality readiness vary. | Make ownership, DMP completeness, and quality explicit before scaling. | P10
Elie Maze | AI, Search and Operations | Aware / API consumer | AI teams need ontology assets through usable APIs. | Expose semantic assets as services for AI and QA. | P11
Pierre Jallais | AI, Search and Operations | Pragmatic consumer | Search quality depends on vocabulary and metadata quality. | Make semantic resources discoverable and usable by search / RAG. | P12
Julien Campan | Operations and Business | Mission-critical consumer | LifeX field evidence does not yet become a semantic decision chain. | Build a V2 data product tied to the weekly decision cycle. | P04, P13, P15, P16

## Priority Action Plan
Phase | Action | Linked pain points | Primary output | Owner | Validation metric
0-30 days | Create TSF portfolio registry and LifeX semantic scope. | P01, P02, P03 | Registry and scoped LifeX semantic data product definition. | TSF semantic authority and OneTech governance | Registry covers priority LifeX concepts, mappings, owners, and consumers.
0-60 days | Build the first LifeX evidence-to-decision semantic chain. | P04, P13, P16 | Traceable pilot decision package. | LifeX owner, TSF modelers, platform teams | One signed question answered with provenance from observation to recommendation.
0-60 days | Agree operating model and RACI. | P09, P10, P14 | Central / domain / platform responsibility model. | OneTech data governance | RACI approved for semantic authority, domain owner, platform consumer, and drift resolution.
30-90 days | Define TSF-to-platform consumption patterns. | P05, P08, P11, P12 | Cognite, Collibra, AI, and search integration patterns. | Platform owners with TSF technical owner | At least one mapping or API pattern demonstrated for LifeX.
60-120 days | Package LifeX as reusable blueprint. | P06, P07, P15 | Reusable LifeX semantic data product blueprint. | LifeX owner, Digital Factory, TSF | Blueprint assessed for reuse on one additional asset, domain, or equipment family.

## Priority Summary
Priority | Count
Critical | 3
High | 9
Medium | 4

## Source Notes
Source | How it was used
Workstream 1 stakeholder perspective summary HTML | Primary source for stakeholder names, layers, postures, signals, asks, and implications.
Archive delivery content | Source for cross-interview pain point framing, missing bridge, LifeX operational workflow, and operating-model gap.
Workstream 4 FAQ and use case showcase | Used to align recommended responses with current TSF / SousLeSens, LifeX, platform, and AI positioning.
WORKSTREAM_DELIVERABLES_CHECKLIST.md | Used to confirm that the standalone pain point matrix was still marked partial.